## Timeline
Yehezkiel's PhD Timeline - ANU RSES (3-year plan)
Enrolment start date |  |  | 2026-09-29
Year 1 Plan + Candidate-Supervisor Agreement due |  |  | 2026-12-28
Confirmation of Candidature (oral) target - month 9 (latest allowed: month 12) |  |  | 2027-06-28
Final seminar to School (6 months before submission) |  |  | 2029-03-28
Target Thesis Submission (3 years) |  |  | 2029-09-28
Scholarship program end (3.5 years) |  |  | 2030-03-28
Maximum Enrolment Period, MEP (4 years) |  |  | 2030-09-28
Maximum Period for Completion, MPC (5 years) |  |  | 2031-09-28
Progress (tasks marked Done) |  |  | 2.273%
ID | Phase | Task | Type | Start M | End M | Start date | End date (due) | Owner | Status | Notes
T01 | 0 Onboarding (M1-3) | ANU mandatory: Rights, Relationships & Respect in Research | Task | 1 | 2 | 2026-09-29 | 2026-11-28 | Me | Not started | ANU requirement in first 3 months
T02 | 0 Onboarding (M1-3) | ANU mandatory: CORE Cultural Learning | Task | 1 | 2 | 2026-09-29 | 2026-11-28 | Me | Not started
T03 | 0 Onboarding (M1-3) | ANU mandatory: University Work Health & Safety (WHS) induction | Task | 1 | 2 | 2026-09-29 | 2026-11-28 | Me | In progress
T04 | 0 Onboarding (M1-3) | ANU mandatory: Code of Conduct | Task | 1 | 2 | 2026-09-29 | 2026-11-28 | Me | In progress
T05 | 0 Onboarding (M1-3) | Research integrity training | Task | 1 | 3 | 2026-09-29 | 2026-12-28 | Me | In progress
T06 | 0 Onboarding (M1-3) | RSES induction + local WHS (whs.rses@anu.edu.au) | Task | 1 | 2 | 2026-09-29 | 2026-11-28 | Me | Not started
T07 | 0 Onboarding (M1-3) | Set up supervisory panel (Chair + advisors) | Task | 1 | 2 | 2026-09-29 | 2026-11-28 | Me + Supervisor | Not started
T08 | 0 Onboarding (M1-3) | Agree expectations with supervisor: feedback turnaround, hours (40 h/wk), WFH vs on-campus, etc | Task | 1 | 1 | 2026-09-29 | 2026-10-28 | Me + Supervisor | Delayed | Common source of misunderstanding - settle early and in writing
T09 | 0 Onboarding (M1-3) | Order computer (up to $2k; supervisor emails HDR Admin if > $2k) | Task | 1 | 2 | 2026-09-29 | 2026-11-28 | Me + Supervisor | Not started | Robyne Anderson orders through IT
T10 | 0 Onboarding (M1-3) | Check milestones in ANUHub (selfservice.sas.anu.edu.au) and eForms | Task | 1 | 1 | 2026-09-29 | 2026-10-28 | Me | Done | Students check ANUHub; supervisors check ANUHub & eForms
T11 | 0 Onboarding (M1-3) | Submit Candidate-Supervisor Agreement + Year 1 Plan | Milestone | 3 | 3 | 2026-11-29 | 2026-12-28 | Me + Supervisor | Not started | Required for 1st Annual Plan. Revisit the Agreement every year, do not 'set & forget'
T12 | 1 Foundation & Confirmation (M1-12) | Literature review | Task | 1 | 6 | 2026-09-29 | 2027-03-28 | Me | Not started | Feeds the CoC thesis proposal
T13 | 1 Foundation & Confirmation (M1-12) | Skills assessment & training plan (part of CoC written component) | Task | 2 | 4 | 2026-10-29 | 2027-01-28 | Me + Supervisor | Not started | Basis for professional development discussion
T14 | 1 Foundation & Confirmation (M1-12) | Develop methodology / pilot tests | Task | 3 | 8 | 2026-11-29 | 2027-05-28 | Me | Not started
T15 | 1 Foundation & Confirmation (M1-12) | Initial results / progress towards results | Task | 5 | 8 | 2027-01-29 | 2027-05-28 | Me | Not started | CoC written component must include initial results
T16 | 1 Foundation & Confirmation (M1-12) | Confirmation Review Panel (CRP) established by Delegated Authority / AD(HDR) | Milestone | 4 | 4 | 2026-12-29 | 2027-01-28 | AD(HDR) | Not started | Follows First Year Plan (+/- 3 months)
T17 | 1 Foundation & Confirmation (M1-12) | Write Thesis Proposal (min 4,000 words: lit review, method, original contribution, initial results, timeline, resources, skills assessment) | Task | 6 | 8 | 2027-02-28 | 2027-05-28 | Me | Not started | Prepared with supervisory panel
T18 | 1 Foundation & Confirmation (M1-12) | Primary Supervisor approves proposal; submit to CRP (>= 10 working days before oral) | Milestone | 8 | 8 | 2027-04-29 | 2027-05-28 | Me + Supervisor | Not started | Hard rule: at least 10 working days before oral presentation
T19 | 1 Foundation & Confirmation (M1-12) | CRP Chair greeting / meeting with candidate (1 month prior to CoC) | Milestone | 8 | 8 | 2027-04-29 | 2027-05-28 | CRP Chair | Not started
T20 | 1 Foundation & Confirmation (M1-12) | Prepare CoC oral presentation (20-30 min + up to 20 min discussion) | Task | 8 | 9 | 2027-04-29 | 2027-06-28 | Me | Not started | Open to all RSES; all CRP members must attend
T21 | 1 Foundation & Confirmation (M1-12) | CoC oral presentation - aim for EARLIER time (month 9) | Milestone | 9 | 9 | 2027-05-29 | 2027-06-28 | Me | Not started | PhD window is 9(-12) months. Deck asks students to aim for the earlier time so amendments still fit
T22 | 1 Foundation & Confirmation (M1-12) | CRP outcome / amendments window (to month 12 latest) | Task | 9 | 12 | 2027-05-29 | 2027-09-28 | CRP / Me | Not started | Outcomes: continue, convert, withdraw, discontinue; amendments -> further CRP review
T23 | 1 Foundation & Confirmation (M1-12) | Attend RSES Thursday seminars (13:00-14:00, J1) and ask questions | Task | 1 | 9 | 2026-09-29 | 2027-06-28 | Me | Not started | Attendance expected as part of CoC; keep going afterwards
T24 | 2 Core research (M9-26) | Year 2 Annual Report / Plan (eForm, bullets, < 2 pages) | Milestone | 12 | 12 | 2027-08-29 | 2027-09-28 | Me + Chair | Not started | Discuss with supervisor/Chair & advisory committee before submitting. If CoC slips near this date, submit together and refer to CoC
T25 | 2 Core research (M9-26) | Main analysis / method application - part 1 | Task | 9 | 18 | 2027-05-29 | 2028-03-28 | Me | Not started
T26 | 2 Core research (M9-26) | Paper 1: draft, submit to journal | Task | 10 | 16 | 2027-06-29 | 2028-01-28 | Me + Supervisor | Not started | Reuse in thesis chapters
T27 | 2 Core research (M9-26) | Main analysis - part 2 / validation | Task | 16 | 24 | 2027-12-29 | 2028-09-28 | Me | Not started
T28 | 2 Core research (M9-26) | Conference presentation (travel support up to $5k via AD(HDR); RSES grant deadline 15 March) | Task | 15 | 20 | 2027-11-29 | 2028-05-28 | Me | Not started | Check ANU/RSES travel grants each year
T29 | 2 Core research (M9-26) | Paper 2: draft, submit to journal | Task | 18 | 26 | 2028-02-29 | 2028-11-28 | Me + Supervisor | Not started
T30 | 2 Core research (M9-26) | Year 3 Annual Report / Plan | Milestone | 24 | 24 | 2028-08-29 | 2028-09-28 | Me + Chair | Not started | Use it to lock the submission date and examiner plan
T31 | 3 Writing & submission (M18-36) | Thesis outline & chapter plan agreed with supervisors | Task | 18 | 19 | 2028-02-29 | 2028-04-28 | Me + Supervisor | Not started
T32 | 3 Writing & submission (M18-36) | Write background & methods chapters (reuse CoC proposal) | Task | 19 | 24 | 2028-03-29 | 2028-09-28 | Me | Not started
T33 | 3 Writing & submission (M18-36) | Write results chapters (reuse papers) | Task | 24 | 30 | 2028-08-29 | 2029-03-28 | Me | Not started
T34 | 3 Writing & submission (M18-36) | Write discussion, conclusions, introduction | Task | 28 | 31 | 2028-12-29 | 2029-04-28 | Me | Not started
T35 | 3 Writing & submission (M18-36) | Final seminar to School (6 months before anticipated submission) | Milestone | 30 | 30 | 2029-02-28 | 2029-03-28 | Me | Not started | PhD Final Seminars: Tuesdays 16:00, J1 Seminar Room
T36 | 3 Writing & submission (M18-36) | Full thesis draft to supervisors / panel | Milestone | 31 | 31 | 2029-03-29 | 2029-04-28 | Me | Not started | Allow supervisors reasonable turnaround time
T37 | 3 Writing & submission (M18-36) | Revisions after supervisor feedback | Task | 32 | 34 | 2029-04-29 | 2029-07-28 | Me + Supervisor | Not started
T38 | 3 Writing & submission (M18-36) | Notification of Intent to Submit (NOI): thesis format, oral exam opt-in, access restriction | Milestone | 34 | 34 | 2029-06-29 | 2029-07-28 | Me | Not started | About 2 months before submission
T39 | 3 Writing & submission (M18-36) | Nomination of Examiners (NOE) | Milestone | 34 | 34 | 2029-06-29 | 2029-07-28 | Me + Supervisor | Not started | About 2 months before submission
T40 | 3 Writing & submission (M18-36) | Pre-submission iThenticate similarity review with supervisor | Task | 35 | 35 | 2029-07-29 | 2029-08-28 | Me + Supervisor | Not started
T41 | 3 Writing & submission (M18-36) | Final formatting & proofread | Task | 35 | 36 | 2029-07-29 | 2029-09-28 | Me | Not started
T42 | 3 Writing & submission (M18-36) | THESIS SUBMISSION: submission form + final upload + supervisor endorsement | Milestone | 36 | 36 | 2029-08-29 | 2029-09-28 | Me | Not started | Scholarship ends at final thesis upload
T43 | 4 Post-submission / buffer | Thesis examination (duration varies); oral exam mandatory if candidature began on/after 1 July 2024 | Task | 37 | 42 | 2029-09-29 | 2030-03-28 | Examiners | Not started | Oral exam optional for candidates who began before July 2024
T44 | 4 Post-submission / buffer | Buffer: scholarship program end at 3.5 years (contingency if anything slips) | Milestone | 42 | 42 | 2030-02-28 | 2030-03-28 | - | Not started | MEP 4 years; MPC 5 years; extensions beyond 4 years are more difficult
Formulas:
Start date = EDATE(D3,[Start M]-1)
End date (due) = EDATE(D3,[End M])-1

## Gantt
Gantt - 42 months (36-month plan + 6-month buffer)
[6 empty] | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3 | [11 empty] | Buffer
ID | Phase | Task | Type | Start M | End M | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42
[6 empty] | Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Apr 27 | May 27 | Jun 27 | Jul 27 | Aug 27 | Sep 27 | Oct 27 | Nov 27 | Dec 27 | Jan 28 | Feb 28 | Mar 28 | Apr 28 | May 28 | Jun 28 | Jul 28 | Aug 28 | Sep 28 | Oct 28 | Nov 28 | Dec 28 | Jan 29 | Feb 29 | Mar 29 | Apr 29 | May 29 | Jun 29 | Jul 29 | Aug 29 | Sep 29 | Oct 29 | Nov 29 | Dec 29 | Jan 30 | Feb 30
T01 | 0 Onboarding (M1-3) | ANU mandatory: Rights, Relationships & Respect in Research | Task | 1 | 2 | 1 | 1
T02 | 0 Onboarding (M1-3) | ANU mandatory: CORE Cultural Learning | Task | 1 | 2 | 1 | 1
T03 | 0 Onboarding (M1-3) | ANU mandatory: University Work Health & Safety (WHS) induction | Task | 1 | 2 | 1 | 1
T04 | 0 Onboarding (M1-3) | ANU mandatory: Code of Conduct | Task | 1 | 2 | 1 | 1
T05 | 0 Onboarding (M1-3) | Research integrity training | Task | 1 | 3 | 1 | 1 | 1
T06 | 0 Onboarding (M1-3) | RSES induction + local WHS (whs.rses@anu.edu.au) | Task | 1 | 2 | 1 | 1
T07 | 0 Onboarding (M1-3) | Set up supervisory panel (Chair + advisors) | Task | 1 | 2 | 1 | 1
T08 | 0 Onboarding (M1-3) | Agree expectations with supervisor: feedback turnaround, hours (40 h/wk), WFH vs on-campus, etc | Task | 1 | 1 | 1
T09 | 0 Onboarding (M1-3) | Order computer (up to $2k; supervisor emails HDR Admin if > $2k) | Task | 1 | 2 | 1 | 1
T10 | 0 Onboarding (M1-3) | Check milestones in ANUHub (selfservice.sas.anu.edu.au) and eForms | Task | 1 | 1 | 1
T11 | 0 Onboarding (M1-3) | Submit Candidate-Supervisor Agreement + Year 1 Plan | Milestone | 3 | 3 |  |  | 1
T12 | 1 Foundation & Confirmation (M1-12) | Literature review | Task | 1 | 6 | 1 | 1 | 1 | 1 | 1 | 1
T13 | 1 Foundation & Confirmation (M1-12) | Skills assessment & training plan (part of CoC written component) | Task | 2 | 4 |  | 1 | 1 | 1
T14 | 1 Foundation & Confirmation (M1-12) | Develop methodology / pilot tests | Task | 3 | 8 |  |  | 1 | 1 | 1 | 1 | 1 | 1
T15 | 1 Foundation & Confirmation (M1-12) | Initial results / progress towards results | Task | 5 | 8 |  |  |  |  | 1 | 1 | 1 | 1
T16 | 1 Foundation & Confirmation (M1-12) | Confirmation Review Panel (CRP) established by Delegated Authority / AD(HDR) | Milestone | 4 | 4 |  |  |  | 1
T17 | 1 Foundation & Confirmation (M1-12) | Write Thesis Proposal (min 4,000 words: lit review, method, original contribution, initial results, timeline, resources, skills assessment) | Task | 6 | 8 | [5 empty] | 1 | 1 | 1
T18 | 1 Foundation & Confirmation (M1-12) | Primary Supervisor approves proposal; submit to CRP (>= 10 working days before oral) | Milestone | 8 | 8 | [7 empty] | 1
T19 | 1 Foundation & Confirmation (M1-12) | CRP Chair greeting / meeting with candidate (1 month prior to CoC) | Milestone | 8 | 8 | [7 empty] | 1
T20 | 1 Foundation & Confirmation (M1-12) | Prepare CoC oral presentation (20-30 min + up to 20 min discussion) | Task | 8 | 9 | [7 empty] | 1 | 1
T21 | 1 Foundation & Confirmation (M1-12) | CoC oral presentation - aim for EARLIER time (month 9) | Milestone | 9 | 9 | [8 empty] | 1
T22 | 1 Foundation & Confirmation (M1-12) | CRP outcome / amendments window (to month 12 latest) | Task | 9 | 12 | [8 empty] | 1 | 1 | 1 | 1
T23 | 1 Foundation & Confirmation (M1-12) | Attend RSES Thursday seminars (13:00-14:00, J1) and ask questions | Task | 1 | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
T24 | 2 Core research (M9-26) | Year 2 Annual Report / Plan (eForm, bullets, < 2 pages) | Milestone | 12 | 12 | [11 empty] | 1
T25 | 2 Core research (M9-26) | Main analysis / method application - part 1 | Task | 9 | 18 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
T26 | 2 Core research (M9-26) | Paper 1: draft, submit to journal | Task | 10 | 16 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
T27 | 2 Core research (M9-26) | Main analysis - part 2 / validation | Task | 16 | 24 | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
T28 | 2 Core research (M9-26) | Conference presentation (travel support up to $5k via AD(HDR); RSES grant deadline 15 March) | Task | 15 | 20 | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1
T29 | 2 Core research (M9-26) | Paper 2: draft, submit to journal | Task | 18 | 26 | [17 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
T30 | 2 Core research (M9-26) | Year 3 Annual Report / Plan | Milestone | 24 | 24 | [23 empty] | 1
T31 | 3 Writing & submission (M18-36) | Thesis outline & chapter plan agreed with supervisors | Task | 18 | 19 | [17 empty] | 1 | 1
T32 | 3 Writing & submission (M18-36) | Write background & methods chapters (reuse CoC proposal) | Task | 19 | 24 | [18 empty] | 1 | 1 | 1 | 1 | 1 | 1
T33 | 3 Writing & submission (M18-36) | Write results chapters (reuse papers) | Task | 24 | 30 | [23 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
T34 | 3 Writing & submission (M18-36) | Write discussion, conclusions, introduction | Task | 28 | 31 | [27 empty] | 1 | 1 | 1 | 1
T35 | 3 Writing & submission (M18-36) | Final seminar to School (6 months before anticipated submission) | Milestone | 30 | 30 | [29 empty] | 1
T36 | 3 Writing & submission (M18-36) | Full thesis draft to supervisors / panel | Milestone | 31 | 31 | [30 empty] | 1
T37 | 3 Writing & submission (M18-36) | Revisions after supervisor feedback | Task | 32 | 34 | [31 empty] | 1 | 1 | 1
T38 | 3 Writing & submission (M18-36) | Notification of Intent to Submit (NOI): thesis format, oral exam opt-in, access restriction | Milestone | 34 | 34 | [33 empty] | 1
T39 | 3 Writing & submission (M18-36) | Nomination of Examiners (NOE) | Milestone | 34 | 34 | [33 empty] | 1
T40 | 3 Writing & submission (M18-36) | Pre-submission iThenticate similarity review with supervisor | Task | 35 | 35 | [34 empty] | 1
T41 | 3 Writing & submission (M18-36) | Final formatting & proofread | Task | 35 | 36 | [34 empty] | 1 | 1
T42 | 3 Writing & submission (M18-36) | THESIS SUBMISSION: submission form + final upload + supervisor endorsement | Milestone | 36 | 36 | [35 empty] | 1
T43 | 4 Post-submission / buffer | Thesis examination (duration varies); oral exam mandatory if candidature began on/after 1 July 2024 | Task | 37 | 42 | [36 empty] | 1 | 1 | 1 | 1 | 1 | 1
T44 | 4 Post-submission / buffer | Buffer: scholarship program end at 3.5 years (contingency if anything slips) | Milestone | 42 | 42 | [41 empty] | 1

## ANU Rules
ANU / RSES rules extracted from the onboarding deck
Area | Requirement (from the deck) | What it means for a 3-year plan | Slide
Program length | Scholarship program end 3.5 yrs; Max Enrolment Period (MEP) 4 yrs (A Dean approves extension); Max Period for Completion (MPC) 5 yrs (PVC Research Training approves). Beyond 4 years, extensions are now more difficult. | Submitting at month 36 leaves ~6 months of scholarship buffer. Do not plan on extensions. | 11-12
First 3 months | ANU requirements: Rights, Relationships & Respect in Research; CORE Cultural Learning; University WHS induction; Code of Conduct. Plus research integrity, RSES induction/WHS, set up supervisory panel. | Finish all compliance items by month 3 so they never block later milestones. | 11-12
Year 1 Plan + Agreement | Yr 1 Plan needs the Candidate-Supervisor Agreement. Many treat it as 'set & forget' but it is a communication tool for every year; paperwork is used if issues escalate to AD(HDR). | Agree feedback turnaround and expectations in writing in month 1-3; revisit yearly. | 11, 18
Confirmation of Candidature (CoC) | A PLAN, not a mid-term review. Goal: check the project is feasible and resources/training are in place. PhD: 9 (-12) months. Aim for the earlier time so the CoC completes on time if amendments are needed. | Target month 9; months 10-12 are the amendment buffer. | 13
CoC written component | Thesis proposal, min 4,000 words, approved by Primary Supervisor, submitted at least 10 working days before the oral. Must include: literature review, methodology, original contribution, initial results, timeline/project plan within program length, resources & funding, accessibility needs (optional), skills assessment. | Have initial results and a realistic 3-year plan ready by month 8. | 14
CoC oral component | 20-30 min presentation + up to 20 min discussion, based on the written proposal, open to all RSES; all CRP members must attend. CRP Chair meets the candidate 1 month prior. Attend RSES seminars. | Book CRP dates early: all panel members must be available. | 13-14
Annual Plan / Report | Yearly eForm: reflect on progress and plans (bullet points, < 2 pages). Discuss with supervisor/Chair and advisory committee before submission; Chair assesses vs previous report; AD(HDR) approves. | Year 2 report ~month 12, Year 3 report ~month 24. | 15-16
Paperwork tip | Submit the RSES annual report at the same time as CoC (or MidTerm Review) and simply refer to it. | If the CoC falls near the annual report date, submit together. | 20
Final stages | Oral presentation to School 6 months before anticipated submission. Notification of Intent to Submit (NOI) and Nomination of Examiners (NOE) about 2 months prior. Pre-submission iThenticate review with supervisor. Submission form + final thesis upload (scholarship ends). Supervisor endorsement. Oral examination mandatory for candidatures that began on/after 1 July 2024. | Final seminar month 30, NOI/NOE month 34, iThenticate month 35, submission month 36. | 17
Progress tracking | Students check ANUHub (selfservice.sas.anu.edu.au); supervisors check ANUHub and eForms. Students are expected to complete milestones on time. | Set calendar reminders from the Timeline dates. | 19
Work hours | 40 hours per week; discuss productivity vs hours and WFH/on-campus with supervisor; AD(HDR) if conflict. Normal hours 08:00-18:00 Mon-Fri; out-of-hours access via Outlook calendar; no work 23:00-06:00. | - | 21
Leave | Recreational leave 4 weeks/year: discuss in writing with Chair & Supervisor, inform HDR Administrator. Program leave (personal/medical/parental): min 1 week per instance, max 2 years total; medical/parental need documentation. | This plan assumes NO program leave. Any program leave would push all dates back. | 22
International candidates | Check visa conditions before applying for program leave; program leave only for 'compelling or compassionate' reasons; expected to be outside Australia while on leave. | Confirm visa conditions and end date against the 3-year plan. | 23
Off-campus candidates | Special forms required; normally 18 months residency at ANU - talk to Robyne & Penny. | If had plan to be off-campus, check this early. | 23
Money & travel | Computer $2k (supervisor emails Robyne for > $2k); stationery from Reception; research support via supervisor; travel support up to $5k administered by AD(HDR). | - | 24
Scholarships & prizes | Vice Chancellor's travel grant; RSES travel grants (deadline March 15): Paterson Fellowship, Sue Kesson, DA Brown Award; Robert Hill Memorial Prize. | Plan conference travel around the 15 March deadline. | 25
Seminars & courses | Thursday School Seminar 13:00-14:00 J1 (attendance expected as part of CoC); PhD Final Seminars Tuesdays 16:00 J1; UG/Master courses can be audited by consulting convener (no registration). | - | 26
Optional development | HDR internships, 3-Minute Thesis (3MT), professional societies, demonstrating (applications twice a year). | Optional: keep them limited so they do not delay the 3-year target. | 27-28
Key contacts | HDR Administrator Robyne Anderson hdr.cosm@anu.edu.au; AD(HDR) Penny King da.hdr.rses@anu.edu.au; RSES WHS whs.rses@anu.edu.au; Counselling +61 2 6215 2211; ANU Security 02 6125 2249; emergency 000 (0-000 from internal phone). | - | 4, 29-30